## Slide 1
MUST Graduate Application Forum
Group members: He Xinyi ,Cao Yulong, Chen Rui, Lu Jie
- Progress Report 2

## Slide 2
Contents
01 | Sprint 2 Progress
02 | Source code
03 | Project Management Process
04 | Challenges Encountered in JIRA+Scrum

## Slide 3
01 | Sprint 2 Progress
Workflow
Active Sprints
Release – Version 2.0
Sprint 2 User Stories

## Slide 4
3 Sprints
Sprint 2
Main Page
Registration
Sprint 1
Sprint 3
Receive Feedbacks
Login Page
Post Text
Separation of Login Page and Registration Page
Change Personal Information
Searching by Keywords
Searching by Tags
(Environment Setting & Database Setting)
Make Comments
Account Management
Session cookie
Give a like

## Slide 5
Workflow

## Slide 6
Active Sprints

## Slide 7
Release – Version 2.0

## Slide 8
Sprint 2 - User Stories We Have Done
1. Separation of Login Page and Registration Page
[sprint1 refine] As a user, I want to separate the login page and the registration page so that I can correctly select the operation I want to perform.
2. Make Comments
As a registered user, I want to comment on other people's posts so that I can learn more relevant information from the sender
3. Account Management
As a registered user, I can log out from the account so that if I can log in again with other accounts
4. Session Cookie
As a registered user, I can be recorded by the website so that I can log in automatically if I accidentally close the browser

## Slide 9
Sprint 2 - User Stories We Have Done
1. Separation of Login Page and Registration Page
[sprint1 refine] As a user, I want to separate the login page and the registration page so that I can correctly select the operation I want to perform.

## Slide 10
Sprint 2 - User Stories We Have Done
2. Make Comments
As a registered user, I want to comment on other people's posts so that I can learn more relevant information from the sender

## Slide 11
Sprint 2 - User Stories We Have Done
3. Account Management
As a registered user, I can log out from the account so that if I can log in again with other accounts

## Slide 12
4. Session cookie – Resolving stateless problem
As a registered user, I can be recorded by the website so that I can log in automatically if I accidentally close the browser
https://global.abb/group/en

## Slide 13
4. Session cookie - Security
Former
Now

## Slide 14
02 | Source Code

## Slide 15
03 | Project Management Process
Burndown chart
Burnup chart
Sprint report
Velocity report

## Slide 16
Burndown Chart
Red line: Number of story points left to complete in sprint 2.
Completed on May 6th.
Fluctuations
Burndown Chart

## Slide 17
Burnup Chart
Red line: Number of story points to be completed in sprint 2.
Green line: Story points completed in sprint 2.
Confluence point: Completed 27 story points, 7 issues before May 6th.
Burnup Chart

## Slide 18
Sprint Report
Issue information:
Issue date, key, type, summary, scope changes
Completed issues
Incomplete issues
Sprint Report

## Slide 19
Velocity Report
Green column: The number of work done in sprint 2.
Total commitment: 39
Total completed: 27
Velocity Report

## Slide 20
04 | Challenges Encountered in JIRA+Scrum

## Slide 21
We only divided issues by the function presented
 Difficult for us to track the implementation of each small function
There are some issues taking relatively long time
The way to solve: divide each issue more carefully in the subsequent sprint.
We forget to create another issue for the issue that need improvement in sprint1
 Lack JIRA related management on this part
The way to solve: confirm what new features we need and is there any room for improvement of previous issues

## Slide 22
We lacked consideration of other factors that might exist when we allocated time
 A lot of work is delayed, the report represents slow before fast, loose before tight
The way to solve: consider some realities when allocating time in the next sprint.

## Slide 23
4. There are some difficulties when we complete Sprint2.
The way to solve: change issues from “abandoned” into “done”

## Slide 24
Daily scrum

## Slide 25
Daily scrum

## Slide 26
Daily scrum

## Slide 27
Daily scrum

## Slide 28
References
Jira productors. (2018, January 9). Jira Documentation, from Jira Documentation: https://confluence.atlassian.com/jira
Erica Chappell. (2020, February 21). What’s A Burn Up Chart & How Do You Use It, from What’s A Burn Up Chart & How Do You Use It: https://clickup.com/blog/burn-up-chart/
Team Asana. (2021, October 11). Burndown chart: What it is and how to use it, from Burndown chart: What it is and how to use it: https://asana.com/resources/burndown-chart
David Lowe. (2017, May 15). Sprint Reports, from Sprint Reports: https://scrumandkanban.co.uk/sprint-reports/
David Lowe. (2022, Feburary 4). Velocity report, from Velocity report: https://docs.microsoft.com/en-us/previous-versions/azure/devops/report/sqlreports/velocity?view=tfs-2017
Caitlin Mackie. (2020, December 15). What is the difference between sprints and versions in Jira, from What is the difference between sprints and versions in Jira: https://www.easyagile.com/blog/sprints-versions-jira/
Luke Harrison. (2021, December 21). How to Create a Forum Website, from How to Create a Forum Website: https://websitesetup.org/create-a-forum-website

## Slide 29: Thanks for listening!